## hingecloser
90 Park Street Brookline
Scope of Work
replace the hinges |  | 1000
replace a closer |  | 450
topcoat the threshold |  | 450
hinges (6) | 160 | 960
closer |  | 770
materials and supplies |  | 120
total |  | 3750

## fnish maint
scope of work |  |  | days | $
| set up |  | 0.5
| test area to select materials |  | 0.5
| Fix any problems with the door |  | 0.5
Prep the Door and the Surrounding woodwork for maintenance topcoat and partial refinish
|  | the door may need to be completely stripped** | 2
|  | some of the woodwork may need to be stripped | 1
|  | mechanically prepare rest of the surface | 1
| make the door adjustment if necessary |  | 0.5
| Topcoat the vestibule door , and the surrounding woodwork |  | 1.5
| Prep and topcoat the threshold on the main door |  | 0.5
|  |  | 8 | 7040
| materials and supplies |  |  | 800
|  | tarps | 100
|  | safety | 100
|  | tape | 25
|  | chemicals | 120
|  | mix cups | 30
|  | rags | 40
|  | finish | 160
|  | miscaleneous | 200
775
| total estimate |  |  | 7840
| ** | current topcoat on the door is very close to pealing off, and may need to be removed before topcoating the door

## topcoat
scope of work |  |  | days | $
| Fix any problems with the door |  | 0.5
color match any repairs to prepare for topcoat
Prep the Door and the Surrounding woodwork for maintenance topcoat
clean the surface
|  | mechanically prepare the surface | 2
| Topcoat the vestibule door, and the surrounding woodwork (matt clear finish) |  | 1.5
| Prep and topcoat the threshold on the main door |  | 0.5
|  |  | 4.5 | 3960
| materials and supplies |  |  | 450
|  | tarps | 100
|  | safety | 100
|  | tape | 25
|  | chemicals | 120
|  | mix cups | 30
|  | rags | 40
|  | finish | 160
|  | miscaleneous | 200
775
| total estimate |  |  | 4410